# Loreweaver Creations Wedding Website

## Accelerated Development and Deployment Plan

Planning date: September 10, 2026
Hard invitation-mailing deadline: Monday, October 19, 2026
Target production-complete date: Saturday, October 17, 2026
Final verification / contingency date: Sunday, October 18, 2026
Available development window: 39 days
Expected dedicated project time: approximately 65–104 hours

# 1. Purpose of This Revised Plan

This plan replaces the remaining sequential development schedule of the previous Wedding Website Development and Deployment Plan.

It does not replace or invalidate the substantive project specifications already completed.

The following existing project documents remain authoritative technical references for their respective subjects:

- requirements.md

- decisions.md

- content-inventory.md

- link-inventory.md

- sitemap.md

- route-inventory.md

- page-outlines.md

- wireframes.md

- rsvp-system-design.md

- rsvp-api-contract.md

- rsvp-example-configurations.json

- rsvp-example-form-schemas.json

- rsvp-test-cases.md

- visual-design-system.md

The purpose of this accelerated plan is solely to replace the previous implementation sequence with one appropriate to the October 19 deadline.

The governing principle from this point forward is:

Existing specifications guide implementation; additional documentation is created only when it directly supports implementation, testing, operation, or an actual changed decision.

The project's success will be measured by the quality, reliability, accessibility, security, privacy, usability, and visual professionalism of the production website rather than by completion of additional planning phases.

# 2. Authoritative Current Project State

## Requirements and information architecture

Complete:

- Website requirements.

- Public and personalized scope.

- Canonical sitemap.

- Canonical browser routes.

- Sticky-navigation structure.

- Page responsibilities.

- Mobile-first low-fidelity wireframes.

- Configuration A and Configuration B behavior.

- Launch-versus-post-wedding scope separation.

No additional sitemap, route, page-outline, or wireframe planning phase is required before coding.

## RSVP system design

Phase 3 is complete through Step 14.

Already finalized:

- Invitation-code normalization.

- Manual invitation-code access.

- Request-body lookup.

- Blank-form response boundary.

- Invitation configuration model.

- Default and reduced question profiles.

- Additional-guest behavior.

- Initial submissions.

- Partial revisions.

- Explicit replacement.

- Explicit zero.

- Explicit clearing.

- Dependency rules.

- Attendance/decline transitions.

- Dietary-response behavior.

- Idempotency.

- Version history.

- Current-response storage.

- Guest confirmation.

- Administrative confirmation.

- Delivery-warning behavior.

- Thirteen React interface states.

- Submission-uncertainty behavior.

- Confirmation-refresh fallback.

- Deadline behavior.

- Privacy requirements.

- Security requirements.

- Rate limits.

- Cache behavior.

- Logging restrictions.

- SMS production gate.

- Data-retention standard.

- Preliminary RSVP test catalog.

The RSVP system therefore moves directly from specification into implementation.

## Production invitation configuration

The authoritative source contains 56 invitation records.

The production transformation rules are already established for:

- invitation code;

- party display/greeting source;

- singular/plural wording mode;

- maximum attendance;

- additional-guest allowance;

- question profile;

- active state;

- environment.

Production-data work must therefore use a repeatable transformation/validation process.

The project will not manually construct 56 separate React forms or hand-code 56 invitation-specific configurations.

## Visual design

visual-design-system.md is complete through Phase 4 Step 6.

Already sufficiently established for implementation:

- visual direction;

- decorative-versus-functional priorities;

- typography roles;

- licensed webfont authorization;

- heading hierarchy;

- semantic colors;

- body color;

- link colors;

- navigation colors;

- button colors;

- status colors;

- focus color;

- readable surfaces;

- provisional spacing scale;

- readable-width tokens.

The remaining visual-design topics will no longer require completion as a large standalone documentation phase before coding.

Instead, button states, form controls, message treatments, focus treatment, navigation details, cards, borders, backgrounds, icons, images, and reduced-motion behavior will be implemented and calibrated in the browser as the corresponding shared components are created.

visual-design-system.md will then be updated only with decisions that become final or materially change.

## Content

Content preparation is now a parallel critical path.

Many functional requirements are finalized but their final guest-facing wording remains unwritten or unverified.

Content therefore falls into three categories.

### A. Specification-derived content

Examples:

- RSVP instructions.

- Validation/error messages.

- Confirmation messages.

- Submission-uncertainty guidance.

- Privacy notices.

- Privacy page.

- FAQ answers derived from finalized decisions.

- Schedule wording.

- Gallery Coming Soon wording.

- Not Found wording.

- External-link notices.

This content can be drafted directly from the governing project documents and should be prepared alongside implementation.

### B. Couple-authored or couple-approved content

Examples:

- Homepage welcome message.

- Our Story.

- Relationship narrative.

- Engagement/wedding-planning narrative.

- Thematic introductory copy.

- Final attire voice and presentation.

This material requires direct couple review and therefore must be prepared earlier than the old schedule anticipated.

### C. Externally dependent content

Examples:

- Final hotel-block property and booking information.

- Warinanco approval-dependent active configuration.

- Current lawful media links.

- Venue/map destinations.

- SMS-provider-specific disclosures if SMS is enabled.

The application must be designed so that these values can be supplied or changed without page redesign.

# 3. Revised Documentation Policy

From this point through invitation launch, documentation work will be deliberately constrained.

## Continue maintaining

### decisions.md

Update only when an established architectural, behavioral, privacy, content-policy, or cross-page decision actually changes.

Do not record routine CSS, component, refactoring, or implementation choices as formal project decisions.

### visual-design-system.md

Use as the design authority.

Do not finish all remaining historical Phase 4 steps as prose before coding.

Instead:

- Implement the outstanding design-system subjects in shared components.

- Test them in the browser.

- Record the resulting reusable rule when necessary.

### content-inventory.md

Use primarily as a content readiness checklist from this point forward.

Do not rewrite completed descriptions merely to keep prose synchronized.

Update status fields when content becomes Ready.

### link-inventory.md

Use as the external-link and asset readiness checklist.

Perform verification when the corresponding page is actually being prepared and once again near launch for volatile destinations.

### README.md

Maintain only the operational information necessary to:

- install dependencies;

- start local development;

- build production;

- understand the source layout;

- configure environment values;

- deploy to Ubuntu;

- avoid production-data/credential exposure.

### Tests

Prefer executable automated tests to additional prose wherever practical.

The existing rsvp-test-cases.md remains the human-readable test authority.

### Launch checklist

Create one concise deployment/security/content/backup/smoke-test checklist.

## Stop requiring

- New planning documents for already specified behavior.

- Separate phase-completion reports.

- Repeated full-document synchronization passes.

- New wireframes for already established pages.

- Additional RSVP behavioral design.

- Redundant inventories.

- Prose documentation of obvious source-tree structure.

- Approval gates between ordinary implementation steps.

- Separate late phases for responsive, accessibility, security, or performance work that belongs inside component implementation.

Target remaining documentation effort before launch: approximately 3–5 hours.

# 4. Invitation-Launch Scope

## Tier 1 — Mandatory

The launch version must contain:

- Home.

- RSVP.

- Theme and Attire.

- Our Story.

- Read, Listen, and Watch.

- Venues.

- Travel.

- Schedule.

- FAQ.

- Gallery — intentional Coming Soon state.

- Privacy.

- Wedding-site Not Found handling.

It must also include:

- Responsive shared layout.

- Compact sticky navigation.

- Accessible mobile menu.

- Licensed project typography.

- Centralized design tokens.

- Centralized public content/configuration.

- Centralized active-event configuration.

- Both approved event configurations.

- Only one publicly active event configuration.

- Manual invitation-code lookup.

- Personalized blank forms.

- Both approved substantive RSVP profiles.

- Zero/one/multiple authorized additional-guest handling.

- Initial submissions.

- Partial revisions.

- Dependency clearing.

- Server-side validation.

- Current-response storage.

- Version history.

- Idempotency.

- Duplicate-submission protection.

- Guest email confirmation.

- Protected administrative email confirmation.

- Delivery-status recording.

- Delivery-warning handling.

- Manual confirmation resend capability.

- Submission-uncertainty safe retry.

- Confirmation route and refresh fallback.

- Deadline enforcement.

- Final-month countdown behavior.

- Private production invitation configuration.

- Google Sheets administrative storage.

- Production/development data separation.

- HTTPS.

- Required rate limits.

- Required cache controls.

- Security headers.

- Guest-safe errors.

- Backend-only credentials.

- Keyboard accessibility.

- Screen-reader-oriented labels and status announcements.

- Responsive phone/tablet/desktop behavior.

- Backup and recovery capability.

- Production operation beneath /wedding/.

- API operation beneath /wedding/api/.

These requirements remain part of the professional baseline.

# 5. Conditional Features and External Dependencies

## Text Message confirmation

Email confirmation is mandatory.

Text Message confirmation remains architecturally supported but is not a launch blocker.

Production must keep Text Message disabled unless:

- a provider has been selected;

- sender configuration is established;

- required provider disclosures are verified;

- credentials remain backend-only;

- authorization wording is complete;

- the complete production flow has been tested successfully.

Until then:

RSVP_SMS_ENABLED=false

The frontend must simply omit the unavailable Text Message option.

SMS may be activated after invitation launch without redesigning the RSVP system.

Any content-inventory entries currently marking SMS-provider-specific material as unconditionally required for launch should be interpreted or later revised to reflect this governing conditional requirement.

## Hotel block

The Travel page is required at launch.

The confirmed hotel-block dates are required.

Property-specific hotel information is displayed once finalized.

If the hotel contract has not been finalized by the website launch date:

- the Travel page remains present and professionally complete;

- the fixed April 30–May 2 hotel-block dates may be stated;

- property-specific information is identified as forthcoming;

- no hotel name, rate, booking link, booking deadline, accessibility claim, or group code is invented.

The content architecture must allow the finalized hotel information to be inserted later without redesigning the Travel page.

## Active event configuration

Both Configuration A and Configuration B must be implemented.

The final active configuration remains an external decision until Warinanco Park approval is resolved.

Implementation must therefore proceed without waiting for that decision.

Before invitations are mailed:

- exactly one configuration must be selected as active;

- all guest-facing configuration-dependent pages must display that same configuration.

A later weather-related switch to Configuration B must not require rebuilding page components.

## Nextcloud

Nextcloud is not a general invitation-launch workstream.

Use Nextcloud before launch only if a specific, approved launch-required wedding-owned download actually requires it.

Wedding-party guide downloads remain recommended rather than mandatory.

Post-wedding gallery storage, guest uploads, full-resolution media, archive organization, and generalized Nextcloud integration are deferred.

# 6. Asset Strategy

Asset work will use a minimum complete curated set, not an exhaustive future asset library.

Launch assets include only material actually required by launch pages.

Priority:

- Homepage hero/introductory artwork.

- Guest color-palette presentation.

- Theme/attire examples and inspiration.

- Any lawful promotional imagery actually used on Read, Listen, and Watch.

- Required venue/map destinations.

- Licensed webfont files.

- Shared decorative assets needed for the final visual shell.

The Theme and Attire page does not require an unnecessarily large inspiration gallery. A smaller carefully selected, rights-reviewed, accessible set is preferable to delaying launch for a comprehensive collection.

The Gallery launch state may remain text-only.

Post-wedding photographs, video assets, albums, gallery thumbnails, and download packages are explicitly outside the invitation-launch asset workload.

# 7. Revised Implementation Workstreams

The former remaining numbered phases are replaced by six deadline-driven workstreams.

## Workstream 1 — Application Foundation, Shared Design Components, and Deployment Proof

Target: September 12–13
Budget: 8–10 hours

### Build the application foundation

Create and configure:

- React/Vite client.

- Node.js/Express server.

- Package manifests and lockfiles.

- Git repository structure.

- .gitignore.

- .env.example files.

- ignored local environment files.

- shared client/server source structure.

Configure:

- /wedding/ Vite base.

- /wedding/api/ client API boundary.

- React Router.

- every canonical browser route.

- wedding-specific Not Found handling.

### Translate the completed design system into code

Create shared style/token files containing:

- typography roles;

- semantic colors;

- spacing tokens;

- readable widths;

- surfaces;

- focus color;

- responsive foundations.

Verify and install only the properly licensed project webfont files.

Implement the remaining Phase 4 subjects directly as reusable shared primitives:

- links;

- primary/secondary buttons;

- form controls;

- status messages;

- focus indicators;

- content cards;

- decorative frames;

- page surfaces.

Do not first write several additional design-system chapters describing components that can be tested more efficiently in the browser.

### Build the shared site shell

Implement:

- page container;

- skip link;

- header;

- sticky navigation;

- mobile menu;

- footer;

- heading system;

- external-link treatment;

- shared CTA treatment.

### Establish centralized content/configuration

Create centralized data structures for:

- couple/wedding basics;

- navigation;

- assistance information;

- event Configuration A;

- event Configuration B;

- active configuration;

- gift policy;

- reusable external resources.

### Early Ubuntu deployment proof

Before proceeding deeply into application features:

- build the client;

- transfer/clone the project to Ubuntu;

- install dependencies independently;

- serve the application beneath /wedding/;

- verify direct navigation and refresh;

- verify an Express test endpoint beneath /wedding/api/;

- verify the reverse proxy/tunnel architecture.

This is a proof of architecture, not final production deployment.

### Parallel content work

During this same weekend, begin:

- Homepage welcome text.

- Homepage CTA copy.

- Our Story drafting.

- RSVP entry/assistance copy derived from specifications.

- Privacy-page draft derived from finalized privacy requirements.

Exit condition: the actual wedding-site shell runs locally, the major design vocabulary exists in code, every canonical route resolves, and the production path has been proven on Ubuntu.

## Workstream 2 — RSVP Backend, Production-Configuration Transformation, and Functional Copy

Target: September 19–20 plus September project workday
Budget: 10–14 hours

Implement against the already finalized RSVP contract.

### Backend

Complete:

- centralized environment validation;

- invitation-code normalization;

- lookup endpoint;

- development fixture loading;

- private configuration service;

- blank-form schema construction;

- submission endpoint;

- backend payload validation;

- initial response creation;

- partial revision merging;

- dependency clearing;

- attendance/dietary rules;

- versioning;

- current-response replacement;

- idempotency;

- duplicate activation protection;

- deadline enforcement;

- rate limits;

- no-store behavior;

- guest-safe errors.

### Data layer

Establish:

- isolated development workbook/store;

- Google Sheets authentication;

- invitation configuration representation;

- current responses;

- version history;

- delivery records.

### Production invitation transformation

Create or use a repeatable transformation process converting the authoritative 56-row source into the approved private production configuration structure.

Validate:

- normalized uniqueness;

- required values;

- singular/plural wording;

- maximum attendance;

- additional-guest allowances;

- supported question profiles;

- production/development separation.

Do not activate real production records during ordinary development.

### Email

Select/configure the production-intended email mechanism sufficiently to implement:

- guest confirmation;

- administrative confirmation;

- independent delivery results;

- manual resend.

### Tests

Implement automated tests alongside each backend responsibility using the existing test catalog and fictional fixtures.

### Parallel content work

Complete or substantially complete specification-derived:

- validation messages;

- error messages;

- service-unavailable copy;

- submission-uncertain copy;

- confirmation copy;

- delivery-warning copy;

- confirmation-refresh fallback;

- RSVP privacy notices;

- email-confirmation template;

- administrative-confirmation template.

Exit condition: the backend can accept a development invitation, return the proper blank form, store an initial RSVP, merge a revision, preserve history, and issue email-confirmation attempts according to the established contract.

## Workstream 3 — Complete RSVP Frontend and Content Lock Round 1

Target: September 26–27
Budget: 9–12 hours

Implement the complete guest-facing RSVP application against the working backend.

Implement all thirteen states:

- Entry Ready.

- Looking Up Invitation.

- Invalid Invitation.

- Service Unavailable.

- Validated Blank Form.

- Validation Failure.

- Submitting.

- Submission Uncertain.

- Confirmed Initial Submission.

- Confirmed Revision.

- Stored with Delivery Warning.

- Confirmation Refresh Fallback.

- RSVP Closed.

Implement:

- default question profile;

- reduced-attendance-dietary profile;

- zero additional guests;

- one additional guest;

- multiple additional guests;

- conditional fields;

- revision semantics;

- safe idempotent retry;

- temporary confirmation-state transfer;

- accessible validation summary;

- focus management;

- progress/status announcements;

- email confirmation selection;

- conditional SMS support without enabling SMS production prematurely.

Responsive and accessible behavior is implemented now rather than deferred.

### Content Lock Round 1

By the end of this workstream, attempt to finalize:

- Home copy.

- RSVP copy.

- Confirmation copy.

- Privacy copy.

- Our Story.

- Theme and Attire prose.

- Schedule prose.

- Gift policy/FAQ copy.

Unresolved externally dependent details may remain pending.

Exit condition: a guest can complete the entire intended RSVP journey on phone and desktop using development data.

## Workstream 4 — Public Pages, Launch Assets, and External Resource Verification

Target: October 3–4
Budget: 10–14 hours

Build the public pages using existing route/page/wireframe specifications.

Complete:

- Home.

- Theme and Attire.

- Our Story.

- Read, Listen, and Watch.

- Venues.

- Travel.

- Schedule.

- FAQ.

- Privacy.

- Gallery Coming Soon.

- Not Found.

### Active-configuration implementation

Verify that Home, Venues, Travel, Schedule, and FAQ all consume the same centralized active configuration.

Test both configurations.

### Assets

Prepare only the curated launch set.

Complete:

- homepage visual;

- guest palette presentation;

- selected outfit/inspiration imagery;

- decorative site assets;

- webfonts;

- any page imagery actually being used.

Perform rights/accessibility/technical review during preparation.

### External links

Research and verify:

- lawful book source(s);

- lawful audiobook source(s);

- lawful film source(s);

- venue maps;

- finalized hotel information if available.

Media availability likely to change should receive another verification immediately before launch.

### Content Lock Round 2

By the end of October 4:

- no ordinary public page should still lack necessary prose;

- remaining unresolved items should be limited primarily to genuine external dependencies.

Exit condition: the entire invitation-launch website is populated and usable locally.

## Workstream 5 — Integrated QA, Production Data Preparation, and Full Deployment Rehearsal

Target: October 10–11 plus October project workday
Budget: 10–12 hours

Former separate responsive, accessibility, performance, security, RSVP-test, and general-test phases are consolidated here.

These are verification passes because their requirements have already been implemented continuously.

### RSVP verification

Execute the controlling RSVP tests covering:

- normalization;

- invalid/inactive codes;

- profiles;

- allowances;

- attendance combinations;

- decline;

- dietary behavior;

- initial submission;

- revisions;

- zero/clear operations;

- idempotency;

- uncertainty/safe retry;

- delivery success/failure;

- confirmation refresh;

- deadline behavior;

- all thirteen states.

### Public-site verification

Test:

- every canonical route;

- unmatched route handling;

- navigation;

- footer;

- direct navigation;

- refresh;

- browser Back/Forward;

- Configuration A;

- Configuration B;

- configuration consistency;

- external links.

### Responsive/accessibility verification

Test representative:

- small phone;

- large phone;

- tablet;

- laptop;

- desktop.

Verify:

- keyboard completion;

- visible focus;

- labels and legends;

- headings;

- validation summary;

- announcements;

- enlarged text;

- reduced motion;

- image alternatives;

- touch targets;

- no horizontal overflow;

- color-independent meaning.

### Security/privacy verification

Verify:

- backend-only invitation data;

- backend-only credentials;

- no production codes in client output;

- no personal RSVP information in URLs;

- no-store behavior;

- no-index transactional routes;

- request validation;

- configured rate limits;

- security headers;

- appropriate logs;

- private Google workbook;

- production/development separation.

### Production invitation data

Generate and review the production configuration from all 56 source records.

Perform automated structural checks rather than manually testing 56 separate interfaces individually.

Use representative/manual checks for exceptional configurations, particularly:

- singular/plural wording;

- allowance 0;

- allowance 1;

- allowances greater than 1;

- reduced question profile.

### Full deployment rehearsal

Execute the intended production procedure on Ubuntu with controlled non-production or isolated validation data.

Document only the steps actually required to reproduce deployment and recovery.

Exit condition: no known architecture, RSVP, content, configuration, accessibility, or deployment issue remains capable of plausibly blocking production cutover.

## Workstream 6 — Feature Freeze, Production Cutover, and Contingency

Target: October 17–18
Budget: 5–7 hours

### Feature freeze

Beginning October 17:

Do not introduce:

- new pages;

- new RSVP behavior;

- new decorative systems;

- new dependencies;

- optional integrations;

- major refactoring.

Only fix:

- launch-blocking defects;

- security/privacy problems;

- accessibility failures;

- incorrect content;

- broken links;

- significant visual problems.

### Production preparation

Finalize:

- active event configuration;

- production invitation configuration;

- production Google workbook;

- production credentials;

- administrative email destination;

- guest email delivery;

- backups;

- production environment values.

If the hotel block is still unresolved, publish the approved pending-information treatment.

If SMS remains incomplete, keep SMS disabled.

### Deploy

Complete:

- production build;

- Ubuntu deployment;

- reverse-proxy configuration;

- HTTPS;

- production security configuration;

- live route verification.

### Live smoke testing

Verify:

- Home and printed QR destination.

- Every navigation destination.

- RSVP code entry.

- Controlled valid lookup.

- Controlled invalid lookup.

- Controlled submission.

- Confirmation email.

- Administrative email.

- Confirmation route.

- Direct nested-route refresh.

- Both desktop and phone presentation.

### Backup/recovery

Verify that:

- current application/configuration is backed up;

- RSVP data is recoverable;

- deployment rollback/recovery procedure is understood.

### October 18

Reserve primarily for:

- final proofreading;

- media/link rechecks;

- QR-code tests from representative phones;

- final production smoke testing;

- launch-blocking corrections.

Production should be complete before the end of Sunday, October 18.

Monday, October 19 is the invitation-mailing date and must not be treated as the planned deployment day.

# 8. Revised Time Budget

| Workstream | Estimated Dedicated Time |
| --- | --- |
| 1 — Foundation, design components, deployment proof | 8–10 hours |
| 2 — RSVP backend, data, production transformation | 10–14 hours |
| 3 — RSVP frontend | 9–12 hours |
| 4 — Public pages, assets, links | 10–14 hours |
| 5 — QA and deployment rehearsal | 10–12 hours |
| 6 — Production cutover | 5–7 hours |
| Core development range | 52–69 hours |
| Protected contingency capacity | 8–12 hours |
| Recommended working requirement | 60–81 hours |

The project's estimated 65–104 available hours therefore provide a viable launch window.

The contingency allowance is intentionally protected.

It must not be consumed early merely because optional visual or technical enhancements are available.

# 9. Priority Rules Under Time Pressure

If available time begins approaching the lower end of the projected range, preserve work in this order:

- RSVP correctness and data integrity.

- Security and privacy.

- Accurate guest information.

- Production deployment and recovery.

- Accessibility.

- Responsive usability.

- Complete public-page content.

- Consistent professional visual design.

- Required curated imagery.

- Additional decorative refinement.

- Recommended downloads.

- SMS confirmation.

- Other optional integrations.

Do not save time by weakening:

- backend validation;

- RSVP testing;

- privacy protections;

- accessibility fundamentals;

- responsive functionality;

- backup/recovery;

- production verification.

Save time first by reducing:

- documentation;

- number of decorative assets;

- optional downloads;

- optional external-resource links beyond a useful minimum;

- ornamental complexity;

- SMS work;

- post-wedding infrastructure.

# 10. Content Management Rule

Because content readiness is now a critical path, content will not wait for “the content phase.”

Every implementation session should resolve relevant copy at the same time.

Where wording is determined by existing specifications, draft it directly from those specifications.

Where wording requires the couple's voice or personal history, batch those decisions so they can be reviewed together rather than interrupting programming repeatedly.

Where information depends on an outside party, implement a configurable pending state rather than waiting to build the page.

The website should never contain temporary developer lorem ipsum after Workstream 4.

# 11. Definition of Invitation-Launch Complete

The invitation-launch version is complete when:

- the production URL works over HTTPS;

- the invitation QR code reaches the correct homepage;

- every required browser route functions;

- nested routes survive direct navigation and refresh;

- navigation works by mouse, keyboard, and touch;

- public content is accurate and professionally presented;

- one event configuration is active consistently;

- the alternate event configuration remains ready for activation;

- unresolved hotel information, if any, is represented accurately rather than invented;

- invitation codes remain private;

- all 56 production source records validate into private configuration;

- development fixtures are disabled in production;

- valid invitation codes return only their permitted blank form;

- invalid invitation codes disclose no private information;

- both approved RSVP profiles function;

- all allowance variants function;

- initial responses store correctly;

- revisions merge correctly;

- dependencies clear correctly;

- current responses and version history are correct;

- duplicate submissions are controlled;

- email confirmation works;

- administrative confirmation works;

- delivery failure does not invalidate stored RSVP data;

- manual resend does not create another RSVP version;

- confirmation and refresh-fallback behavior works;

- deadline behavior is backend-authoritative;

- forms are keyboard-operable;

- validation/status information is accessible;

- phone, tablet, and desktop layouts are usable;

- production invitation/configuration data is absent from frontend bundles;

- credentials are absent from source control;

- personalized responses are not publicly cached;

- transactional routes are not indexed;

- required rate limiting and security protections operate;

- backups exist and recovery has been exercised;

- external launch links have been verified;

- no known launch-blocking defects remain.

SMS confirmation is not part of this completion test unless the SMS production gate has been deliberately satisfied and the feature has been enabled.

Final hotel-property details are not part of this completion test until a property/block actually exists to publish, provided the Travel page accurately communicates the current state.

# 12. Post-Launch Work

After invitations are mailed, optional and future development may include:

- SMS-provider implementation and activation.

- Final hotel information if still pending.

- Additional attire/inspiration content.

- Additional decorative refinement.

- Wedding-party downloads.

- Additional Nextcloud-backed resources.

- Post-wedding gallery.

- Guest uploads.

- Full-resolution media access.

- Video publishing.

- Long-term wedding archive.

- RSVP retirement after the RSVP lifecycle ends.

None of these activities may retroactively delay the October 19 invitation launch.